Family Travel App

Development Roadmap

Timeline 10 weeks to MVP launch Team Adam (Backend/AI) + Sairam (Mobile/Frontend) Stack Expo • Supabase • Gemini API • ElevenLabs Launch City Paris (expand to NYC, London post-MVP)

01  Vibecode Philosophy

Maximize AI-assisted development. Ship fast, iterate based on feedback.

| Instead of... | Vibecode with... |
| --- | --- |
| Custom auth system | Supabase Auth — Google/Apple sign-in in 10 minutes |
| PostgreSQL + Redis setup | Supabase (Postgres) + Upstash (Redis) — free tiers |
| Custom REST API | Supabase auto-generated APIs + Edge Functions |
| React Native from scratch | Expo + Cursor — describe screens, AI scaffolds |
| Complex CI/CD | Expo EAS + Vercel — push to deploy |
| Audio processing pipeline | ElevenLabs API — single API call |
| Geofencing from scratch | expo-location — built-in geofencing |

02  Timeline Overview

| Week | Phase | Adam | Sairam |
| --- | --- | --- | --- |
| 1 | Setup | Supabase, Gemini config | Expo project, auth UI |
| 2–3 | Trip Planning | Itinerary AI, Viator API | Planning wizard, display |
| 4–5 | Location Audio | Narrations, TTS, caching | Map, geofencing, player |
| 6–7 | Scavenger Hunt | Vision challenges, scoring | Camera, progress UI |
| 8–9 | Polish | Content, monitoring | Offline, animations |
| 10 | Launch | Load testing, alerts | App Store, TestFlight |

03  Week-by-Week Breakdown

WEEK 1 Setup & Scaffolding Goal: Working app shell with auth. Both devs can run locally.

| Adam (Backend/AI) | Sairam (Mobile/Frontend) |
| --- | --- |
| ○ Create Supabase project ○ Set up tables: users, families, trips ○ Configure Google/Apple OAuth ○ Create Gemini API wrapper ○ Set up Upstash Redis | ○ Init Expo project (TypeScript) ○ Set up React Navigation ○ Build auth screens ○ Connect Supabase auth ○ Create home screen shell |

✓ Demo: User signs in with Google → sees empty home screen

WEEK 2–3 Trip Planning Engine Goal: User inputs trip details → gets AI itinerary with ticket links.

| Adam (Backend/AI) | Sairam (Mobile/Frontend) |
| --- | --- |
| ○ Build Gemini itinerary prompt ○ Parse response → structured data ○ Integrate Viator API ○ Create /trips endpoint ○ Store trips in Supabase ○ Handle errors gracefully | ○ Trip creation wizard UI ○ Google Places autocomplete ○ Interest picker component ○ Party size/ages input ○ Itinerary display screen ○ Day-by-day timeline view ○ Ticket link buttons |

✓ Demo: Create '3 days in Paris with kids' → see full itinerary with Louvre tickets

WEEK 4–5 Location-Aware Audio Goal: Walking near Eiffel Tower triggers audio narration.

| Adam (Backend/AI) | Sairam (Mobile/Frontend) |
| --- | --- |
| ○ Build narration prompt ○ Integrate ElevenLabs TTS ○ Create /narration endpoint ○ Cache audio URLs (24hr) ○ Pre-generate top 20 Paris POIs ○ Create POI database | ○ Map view with itinerary pins ○ expo-location permissions ○ Geofencing (100m radius) ○ Background location task ○ Audio player component ○ Mini-player UI ○ Proximity notifications |

✓ Demo: Simulate GPS near Eiffel Tower → hear 60-second narration

WEEK 6–7 Scavenger Hunt Goal: Point camera at exhibit → get challenge → earn points.

| Adam (Backend/AI) | Sairam (Mobile/Frontend) |
| --- | --- |
| ○ Gemini Vision challenge prompt ○ /challenges/generate endpoint ○ Parse challenge JSON ○ /challenges/answer endpoint ○ Scoring logic (10 pts each) ○ Badge award system | ○ Camera screen (expo-camera) ○ 'Scan exhibit' capture button ○ Challenge card UI ○ Hint toggle ○ Answer input + submit ○ Success/fail animations ○ Progress screen ○ Badge unlock modal |

✓ Demo: Photo of Mona Lisa → 'Find the hidden bridge' challenge → answer → earn 10 points

WEEK 8–9 Polish & Content Goal: App feels complete. Works offline. Paris content ready.

| Adam (Backend/AI) | Sairam (Mobile/Frontend) |
| --- | --- |
| ○ Pre-generate all Paris content ○ Rate limiting (60 RPM/user) ○ Error monitoring (Sentry) ○ API optimization ○ Fallback content ○ Database indexes | ○ Offline mode (cache trip) ○ Loading skeletons ○ Error handling UI ○ Animations (Reanimated) ○ Haptic feedback ○ App icon + splash ○ Bug bash + QA |

✓ Demo: Full Paris trip flow in airplane mode after initial sync

WEEK 10 Launch Prep Goal: App in TestFlight, ready for beta users.

| Adam (Backend/AI) | Sairam (Mobile/Frontend) |
| --- | --- |
| ○ Load testing (k6) ○ Supabase alerts ○ Database backups ○ API documentation ○ Cost monitoring | ○ App Store Connect setup ○ Screenshots + preview video ○ Privacy policy page ○ TestFlight build ○ Invite 10–20 beta testers |

✓ Demo: App approved and live in TestFlight with first beta users

04  Risk Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Gemini API latency | Slow generation | Pre-cache top 50 POIs, skeleton UI |
| Viator API delayed | No ticket links | Fallback to Google search links |
| Geofencing unreliable | Missed triggers | Add manual 'I'm here' button |
| App Store rejection | Launch delay | Submit week 9, budget fix time |
| Scope creep | Missed deadline | Strict MVP: Paris only, scavenger only |

05  Monthly Cost Estimate

| Service | Free Tier | At 1K Users |
| --- | --- | --- |
| Supabase (DB + Auth) | 500MB, 1GB storage | ~$25/mo |
| Gemini API | Generous free tier | ~$50–100/mo |
| ElevenLabs TTS | 10K chars/mo | ~$22/mo |
| Upstash Redis | 10K cmds/day | ~$10/mo |
| Expo EAS | 30 builds/mo | Free tier |
| TOTAL | $0 during dev | ~$100–150/mo |

06  MVP Success Criteria

●  20 beta users complete a Paris trip end-to-end

●  Trip creation latency under 5 seconds

●  80% of audio narrations trigger correctly

●  50+ scavenger challenges completed across all users

●  No critical bugs reported in week 10

●  App Store approval on first or second submission

07  Post-MVP Roadmap

Only after MVP is stable with user feedback:

| Weeks | Feature | Why |
| --- | --- | --- |
| 11–12 | NYC + London content | Expand addressable market |
| 13 | Family leaderboards | Most requested feature |
| 14 | Interactive roleplay mode | Competitive differentiation |
| 15–16 | Trip sharing + social | Viral growth potential |